Plan of action for decision VII/8o (Romania)

Through paragraph 3 (a) of decision VII/8o concerning the compliance of Romania, the Meeting of the Parties to the Aarhus Convention has requested the Party concerned to submit a plan of action, including a time schedule, to the Committee by 1 July 2022 regarding the implementation of the recommendations contained in that decision.

The text of decision VII/8o is available at: <https://unece.org/env/pp/cc/decision-vii8o-concerning-romania>

In preparing its plan of action, the Party concerned was invited by the Compliance Committee to take into account the Committee’s information note for Parties on preparing their plan of action. The Committee’s information note, which contains step-by-step guidance for Parties on how to complete their plan of action, is available at: <https://unece.org/env/pp/cc/implementation-decisions-meeting-parties-compliance-individual-parties>

|  |  |
| --- | --- |
| **A. Description of the process by which the plan of action has been prepared** | |
|  | |
| **B. General character of the measures that will be needed to implement the recommendations in the MOP decision** | |
|  | |
| **C. Detailed plan of action** | |
| **Recommendation:**  **Para. 2 (a) (i) of decision VII/8o** | In paragraph 2 (a) (i) of decision VII/8o, the Meeting of the Parties requests that the Party concerned:   1. Provide the Committee with evidence that it has, as a matter of urgency, taken the necessary legislative, regulatory and administrative measures and practical arrangements to ensure that public officials:      1. Respond to requests of members of the public to access environmental information as soon as possible, and, at the latest, within one month after the request was submitted, and, in the case of a refusal, state the reasons for the refusal; |
| Proposed measures to fulfil recommendation | Noi acțiuni de diseminare informații din „Ghidul pentru Autoritățile Publice pentru Accesul Public la Informațiile de Mediu". *- Propuneri de acțiuni de informare din partea autorităților*  Chestionar pentru autoritățile publice pentru aflarea problemelor întâmpinate în implementarea Convenției |
| Outline of the steps necessary to implement the proposed measures | Noi acțiuni de informare a autorităților publice cu privire la ghid  Realizare, transmitere și colectare răspunsuri la chestionar |
| Actors involved | MMAP  Alte autorități publice |
| Final date by when implementation of recommendation will be completed | Final 2022 |
| **Recommendation:**  **Para. 2 (a) (ii) a. of decision VII/8o** | In paragraph 2 (a) (ii) a. of decision VII/8o, the Meeting of the Parties requests that the Party concerned:   1. Provide the Committee with evidence that it has, as a matter of urgency, taken the necessary legislative, regulatory and administrative measures and practical arrangements to ensure that public officials: 2. Correctly implement the Convention with respect to: 3. Article 2 (3) – the definition of “environmental information”; |
| Proposed measures to fulfil recommendation | Noi acțiuni de diseminare informații din „Ghidul pentru Autoritățile Publice pentru Accesul Public la Informațiile de Mediu". *- Propuneri de acțiuni de informare din partea autorităților*  Chestionar pentru autoritățile publice pentru aflarea problemelor întâmpinate în implementarea Convenției |
| Outline of the steps necessary to implement the proposed measures | Noi acțiuni de informare a autorităților publice cu privire la ghid  Realizare, transmitere și colectare răspunsuri la chestionar |
| Actors involved | MMAP  Alte autorități publice |
| Final date by when implementation of recommendation will be completed | Final 2022 |
| **Recommendation:**  **Para. 2 (a) (ii) b. of decision VII/8o** | In paragraph 2 (a) (ii) b. of decision VII/8o, the Meeting of the Parties requests that the Party concerned:   1. Provide the Committee with evidence that it has, as a matter of urgency, taken the necessary legislative, regulatory and administrative measures and practical arrangements to ensure that public officials:   (ii) Correctly implement the Convention with respect to:   1. Article 4 (6) – the requirement to separate confidential from nonconfidential information whenever possible and to make available the latter; |
| Proposed measures to fulfil recommendation | Noi acțiuni de diseminare informații din „Ghidul pentru Autoritățile Publice pentru Accesul Public la Informațiile de Mediu". *- Propuneri de acțiuni de informare din partea autorităților*  Chestionar pentru autoritățile publice pentru aflarea problemelor întâmpinate în implementarea Convenției |
| Outline of the steps necessary to implement the proposed measures | Noi acțiuni de informare a autorităților publice cu privire la ghid  Realizare, transmitere și colectare răspunsuri la chestionar |
| Actors involved | MMAP  Alte autorități publice |
| Final date by when implementation of recommendation will be completed | Final 2022 |
| **Recommendation:**  **Para. 2 (a) (iii) of decision VII/8o** | In paragraph 2 (a) (iii) of decision VII/8o, the Meeting of the Parties requests that the Party concerned:   1. Provide the Committee with evidence that it has, as a matter of urgency, taken the necessary legislative, regulatory and administrative measures and practical arrangements to ensure that public officials:      1. Interpret the grounds for refusing access to environmental information in a restrictive way, taking into account the public interest served by disclosure, and, in stating the reasons for a refusal, specify how the public interest served by disclosure was taken into account; |
| Proposed measures to fulfil recommendation | HG. 878/2005 privind accesul publicului la informaţia privind mediul, art. 15, alin. (3) prevede că „Respingerea cererii de furnizare a informaţiilor privind mediul conţine motivele refuzului, precum şi informaţiile privind procedura de revizuire prevăzută la art. 16 – 19”. Dispoziția este incompletă, raportată la Decizia VI/8o, alin. (2), lit. (a) (ii) a. și b. Astfel, raportat la alin. 2, lit. (a) (iii) al Deciziei, se va impune ca necesară completarea alineatului, astfel încât refuzul să prevadă expres și cerința de menționare din partea autorităților publice a modului în care a fost luată în calcul satisfacerea interesului public în legătură cu dezvăluirea informației.  Modificare Ordin nr. 1182 din 18 decembrie 2002 pentru aprobarea Metodologiei de gestionare și furnizare a informației privind mediul, deținută de autoritățile publice pentru protecția mediului. |
| Outline of the steps necessary to implement the proposed measures | Inițierea modificării legislative de către MMAP. Avizare internă, externă și consultarea publicului. |
| Actors involved | MMAP, alte ministere  publicul |
| Final date by when implementation of recommendation will be completed | 1,5 ani |
| **Recommendation:**  **Para. 2 (b) of decision VII/8o** | In paragraph 2 (b) of decision VII/8o, the Meeting of the Parties requests that the Party concerned:   1. Provide the Committee with evidence that it has provided training to public authorities about the above duties; |
| Proposed measures to fulfil recommendation | Diseminare informații privind modificările legislative |
| Outline of the steps necessary to implement the proposed measures | Transmitere informări către autoritățile publice |
| Actors involved | MMAP |
| Final date by when implementation of recommendation will be completed | 1.5 ani |
| **Recommendation:**  **Para. 2 (c) of decision VII/8o** | In paragraph 2 (c) of decision VII/8o, the Meeting of the Parties requests that the Party concerned:   1. Review its legal framework in order to identify cases where decisions to permit activities within the scope of article 6 of the Convention are conducted without effective participation of the public (art. 6 (3) and (7)), and to take the necessary legislative and regulatory measures to ensure that such situations are adequately remedied; |
| Proposed measures to fulfil recommendation | Crearea cadrului pentru participarea publicului în procedura de emitere a **certificatelor de descărcare de sarcină arheologică** emise de structurile din subordinea Ministerului Culturii *– soluții propuse de MC*  Crearea cadrului pentru participarea publicului în procedura de emitere **a licențelor miniere**, emise de Agenția Națională pentru Resurse Minerale. *– soluții propuse de ANRM*  (*Survey)* Analiza de către fiecare autoritate emitentă a procedurilor de emitere a diferitelor acte de reglementare/avize/acorduri/decizii/autorizații/certificate/licențe/etc. pentru activitățile prevăzute de Anexa I a Convenției Aarhus, în scopul identificării acelor proceduri pentru care trebuie asigurată participarea publicului, conform art. 6 al Convenției. *– de completat cu acte de reglementare/avize/acorduri/decizii/autorizații/certificate/licențe/etc. emise de autorități centrale/autorități subordonate* |
| Outline of the steps necessary to implement the proposed measures |  |
| Actors involved | Ministerul Culturii  ANRM  alte autorități publice |
| Final date by when implementation of recommendation will be completed | 2 ani |
| **Recommendation:**  **Para. 2 (d) of decision VII/8o** | In paragraph 2 (d) of decision VII/8o, the Meeting of the Parties requests that the Party concerned:  (d) Review its legal framework and undertake the necessary legislative, regulatory and administrative measures to ensure that the court procedures for access to environmental information are timely and provide adequate and effective remedies; |
| Proposed measures to fulfil recommendation | Identificarea de soluții pentru fluidizarea rezolvării dosarelor în instanțele naționale în ceea ce privește accesul la informația de mediu, cu accent pe acordarea priorității în privința cazurilor ce au ca obiect negarea accesului la informația de mediu și pe fixarea unui termen determinat înăuntrul căruia instanțele judecătorești să soluționeze cazurile*. – solutii propuse de Ministerul Justiției* |
| Outline of the steps necessary to implement the proposed measures |  |
| Actors involved | Ministerul Justiției |
| Final date by when implementation of recommendation will be completed | 2023 |
| **Recommendation:**  **Para. 2 (e) of decision VII/8o** | In paragraph 2 (e) of decision VII/8o, the Meeting of the Parties requests that the Party concerned:  (e) Provide adequate practical arrangements or measures to ensure that the activities listed in subparagraphs (a)–(d) above are carried out with broad participation of the public authorities and the public concerned; |
| Proposed measures to fulfil recommendation | Diseminarea pe site-ul MMAP a acțiunilor întreprinse |
| Outline of the steps necessary to implement the proposed measures |  |
| Actors involved | MMAP |
| Final date by when implementation of recommendation will be completed | la momentul fiecărei acțiuni |